DISSOLUTION OF LLANDOUGH COMMUNITY COUNCIL AND MICHAELSTON LE PIT AND LECKWITH COMMUNITY COUNCIL AND CREATION OF LLANDOUGH AND CWRTYRALA COMMUNITY COUNCIL

JOINT PROJECT PLAN

KEY FOCUS AREA - PEOPLE

| Activity | Requirement | Schedule of Actions | Responsibility | Target Date |
| --- | --- | --- | --- | --- |
| Compile record of contracts of employment including job descriptions, salary grades and related matters | Both serving clerks to share information with each other to create this information source. The employees affected are the part-time clerks of both current councils and the part-time caretaker employed by LCC | Keep the records on a shared file | Both Clerks | 31 January 2027 |
| Issue TUPE transfer letters to three members of staff – each current council to activate (model letters supplied by One Voice Wales) | Employees have a right to transfer under their current terms and conditions (none of the staff contribute to a pension scheme | Letters to be issued | Both Chairs with support from Clerks | 31 January 2027 |
| LCC to consider position of its serving Clerk who has indicated his desire to retire after the transfer – he has indicated that he would be willing to remain in post until such time as the permanent staffing position of the new council is resolved | Develop a staffing model for the roles of Clerk and RFO to include job descriptions and working methods | Enable the transfer of the three staff to the new council Resolve the issue of the payment of a gratuity payment to the LCC Clerk post transfer (There is a ringfenced reserve in the LCC accounts and legal advice in relation to the payment) | Chair of new Council with the RFO | 31 August 2027 |

KEY FOCUS AREA – FINANCE

| Activity | Requirement | Schedule of Actions | Responsibility | Target Date |
| --- | --- | --- | --- | --- |
| Take care in use of reserves as they might be required to support the council in its first year | Both councils to review the use of reserves and ensure that they are transferred to the new council | Discussions between Chairs and Clerks in this regard | Chairs/Clerks – to be endorsed by existing councils | 31 March 2027 |
| Identify Banking Provider | As both current councils use Barclays Bank a plan to be prepared to transfer funds into the new council’s account | Discussion with Barclays Bank. Ask Barclays what evidence they require for a community council account. Prepare draft bank mandate forms. Determine creditor payment method (LCC use cheque payments and MLCC use bank transfer payments) Prepare identity verification requirements for proposed signatories once known. Prepare draft resolutions for appointment of signatories. | Clerks New Council Clerks | 31 January 2027 31 May 2027 28 February 2027 |
| Budget Preparation | As current councils are unable to set a precept for 2027/28 (The Welsh Ministers will notify the precept to the county borough council) current councillors can only prepare a draft budget which will need to be reviewed by the new council based on the level of precept received | Both current councils to prepare a draft budget for 2027/28 but cannot set a precept. This will need to be amalgamated for consideration by the new council. | Councils | 31 December 2026 |
| Close accounts for the period up to the date of dissolution ready for auditing (The responsibility will be assumed for processing the accounts by the new council) | All relevant documentation to be completed as early as possible and annual returns to be approved by the new council. | Clerks to give this matter priority | Clerks | 31 May 2027 |
| Notify HMRC of change of creation of new council and reconfiguration of Basic PAYE Tools | Both councils use Basic PAYE Tools for processing salaries and need to agree approach about how to maintain the system post dissolution | Clerks | Clerks | 31 March 2027 |
| Decide on form of accounts | To decide whether to continue with the Advantage Edge bespoke accounting system | Clerks to discuss and come to a preferred position | Clerks/Councils | 28 February 207 |

7

KEY FOCUS AREA – COMMUNICATION AND COMMUNITY ENGAGEMENT

| Activity | Requirement | Schedule of Actions | Responsibility | Target Date |
| --- | --- | --- | --- | --- |
| Website | Both councils have websites supplied by Vision ICT – these will transfer as an asset to the new council and a new website should have a link to the old websites with a note to state that they will not be updated after the date of dissolution | Discuss with Vision ICT arrangements for the creation of a new website for the new council with links to the former websites – discussion required on cost sharing | Clerks/councils | 28 February 2026 (New website to be operational from the date of dissolution) |
| Community Information | Current councils to notify residents of creation of a new council It is noted that LCC currently prepare quarterly newsletters hand delivered to households | Method of communication to be determined New council to consider whether to continue with quarterly newsletters | Councils/Clerks | 31 March 2027 |
| Hosted email addresses | To decide on whether to continue with Vision ICT system which both councils currently use | Need to have discussions with Vision ICT | Councils/Clerks | 28 February 2027 |

KEY FOCUS AREA – CIVIC RECOGNITION

| Activity | Requirement | Schedule of Actions | Responsibility | Target Date |
| --- | --- | --- | --- | --- |
| Decision required on use of civic regalia | To consider chains or badge of office for Chair, Vice Chair and Consort | Both councils have their own civic regalia | New Council | 30 June 2027 |
| Consider whether to arrange an annual Civic Service | LCC has historically arranged an annual Civic Service | New Council to consider future arrangements | New Council | 30 June 2027 |

KEY FOCUS AREA – ASSETS

| Activity | Requirement | Schedule of Actions | Responsibility | Target Date |
| --- | --- | --- | --- | --- |
| Need to combine asset registers | Create one asset register | Clerks to integrate the asset registers | Clerks | 28 February 2027 |

KEY FOCUS AREA – INSURANCE

| Activity | Requirement | Schedule of Actions | Responsibility | Target Date |
| --- | --- | --- | --- | --- |
| Need to determine insurance arrangements for new council ensuring that current insurance cover existing councils up to the date of dissolution | Need to amalgamate requirements for new council and obtain quotations | Both councils are insured with Zurich and they need to be informed of the change and invited to quote | Clerks | 31 March 2027 |

KEY FOCUS AREA – GOVERNANCE

| Activity | Requirement | Schedule of Actions | Responsibility | Target Date |
| --- | --- | --- | --- | --- |
| Storage of Signed Minutes | Suggest all are stored in Glamorgan Records Office | Councils to decide on course of action | Clerks/Councils | 28 February 2027 |
| Arrangement of first meeting of the new council | This will be arranged by the proper officer of the Vale of Glamorgan Council | Agenda items to be included on the agenda are suggested as: Election of Chair Apologies and Declarations of Interest Confirmation of legal establishment of the council Adoption of the code of conduct Appointment of Clerk whether interim or substantive Appointment of RFO Appointment of Internal Auditor Adoption of standing orders Adoption of financial regulations Approval of banking arrangements and signatories Insurance arrangements Receipt of asset and liability transfer information Appointment of principal trustees to serve on the Llandough and Leckwith War Memorial Hall Management Committee Receipt of precept and budget information Approval of initial expenditure required to operate the council Website, email and publication arrangements Future meeting dates Forward work programme (It is suggested that an ordinary meeting of the new council appoints committees and representatives to serve on external bodies |  |  |
| Agree location of meetings | To decide on location of meetings | Llandough and Leckwith War Memorial Hall Council Chamber offers hybrid meeting facilities | Councils | 28 February 2027 |

KEY FOCUS AREA – LEGAL CHANGES

| Activity | Requirement | Schedule of Actions | Responsibility | Target Date |
| --- | --- | --- | --- | --- |
| Need to change all signposting | Determine signs to be changed | Each council to decide on which signs require changing | Councils | 28 February 2027 |
| All title deeds and licences to be changed | May need to engage solicitors | LCC only owns land and has a licence on the Corbett Road allotments site. Land owned by LCC is as follows: - Village Green No. 41-Registered Parcel of Land Common Commissioners Letter in Clerk’s File - Corbett Road Allotments Annual Licence - Village Garden (Off Penlan Road) Title Deeds with Merrils Ede - Brook Green Title Deeds in Clerk’s File - Village Green - (Extended Parcel) Title Deeds with Merrils Ede - Lewis Road Allotments Title Deeds with Merrils Ede - Llandough and Leckwith Hall Title Deeds Title Deeds with Slater and Gordon - Lease on land for MUGA in King George V Memorial Playing Fields Lease with Merrils Ede (Penarth)Period of 25 years from November 2019 |  |  |

KEY FOCUS AREA – LIABILITIES AND COMMITMENTS

| Activity | Requirement | Schedule of Actions | Responsibility | Target Date |
| --- | --- | --- | --- | --- |
| LCC has a grounds maintenance contract which covers the period 2026 to 2030 | Possibly add in the grass cutting of the Leckwith Common | Clerks to discuss | Councils | 28 February 2027 |
| LCC is committed to developing a new allotments site off Lewis Road | To review progress and develop an action plan for implementation | Clerks to discuss | Councils | 31 March 2027 |

KEY FOCUS AREA – MAINTENANCE CONTRACTS

| Activity | Requirement | Schedule of Actions | Responsibility | Target Date |
| --- | --- | --- | --- | --- |
| Inspection arrangement for play equipment/MUGA for LCC managed by Vale of Glamorgan Council | Agree continuation with Vale of Glamorgan Council | LCC Clerk to secure continuation | LCC Clerk | 28 February 2027 |
| Annual Tree Surveys required in Llandough | Ensure they are continued as they are a condition of insurers | New Council to ensure they are undertaken | Clerks | Ongoing |

KEY FOCUS AREA – MISCELLANEOUS

| Activity | Requirement | Schedule of Actions | Responsibility | Target Date |
| --- | --- | --- | --- | --- |
| Intentionally blank |  |  |  |  |